## Mid Range Fee Justification
Fee Justification
Project | City of Lawrence Task order 13 CCMG 2024-02 Resurfacing Program | [5 empty] | Contractor: | Howard Companies
Des. Number | NA | [5 empty] | Const. Est: | 893821.15
Contract Number | NA | [5 empty] | Letting
Location | City of Lawrence, Various locations
Task Description | [6 empty] | Subconsultant or Vendor | Expenses | Total
|  | PM5 | Inspector 2 | Mileage
|  | 225.5403 | 127.2803 | 0.5
2024-2 Resurfacing Program
Reimbursable Expense i.e Mileage |  | 0 | 0 | 40 |  |  | 0 | 0 | 20
Project Management |  | 20 | 0 |  |  |  | 0 | 0 | 4510.8051
Preconstruction, Progress Meetings |  | 14 | [6 empty] | 3157.5635
Inspection / Measure / Quantify Items |  |  | 440 | [5 empty] | 56003.3314
Red-Line As-Built Drawings (required) & As-Built Digital Data Submission (if applicable) |  |  | 10 | [5 empty] | 1272.803
Final Construction Record | [8 empty] | 0
Subtotal |  | 34 | 450 | 40 | 0 | 0 | 0 | 0 | 64964.5029
Rounded Subtotal | [8 empty] | 65000
Total Cost | [8 empty] | 65000
Total Hours |  | 524

## Low Range Fee Justification
Fee Justification
Project | City of Lawrence Task order 13 CCMG 2024-02 Resurfacing Program | [5 empty] | Contractor: | Howard Companies
Des. Number | NA | [5 empty] | Const. Est: | 893821.15
Contract Number | NA | [5 empty] | Letting
Location | City of Lawrence, Various locations
Task Description | [6 empty] | Subconsultant or Vendor | Expenses | Total
|  | PM5 | Inspector 2 | Mileage
|  | 225.5403 | 127.2803 | 0.5
2024-2 Resurfacing Program
Reimbursable Expense i.e Mileage |  | 0 | 0 | 40 |  |  | 0 | 0 | 20
Project Management |  | 20 | 0 |  |  |  | 0 | 0 | 4510.8051
Preconstruction, Progress Meetings |  | 10 | [6 empty] | 2255.4025
Inspection / Measure / Quantify Items |  |  | 330 | [5 empty] | 42002.4985
Red-Line As-Built Drawings (required) & As-Built Digital Data Submission (if applicable) |  |  | 10 | [5 empty] | 1272.803
Final Construction Record | [8 empty] | 0
Subtotal |  | 30 | 340 | 40 | 0 | 0 | 0 | 0 | 50061.5091
Rounded Subtotal | [8 empty] | 50100
Total Cost | [8 empty] | 50100
Total Hours |  | 410

## Upper Range Fee Justification
Fee Justification
Project | City of Lawrence Task order 13 CCMG 2024-02 Resurfacing Program | [5 empty] | Contractor: | Howard Companies
Des. Number | NA | [5 empty] | Const. Est: | 893821.15
Contract Number | NA | [5 empty] | Letting
Location | City of Lawrence, Various locations
Task Description | [6 empty] | Subconsultant or Vendor | Expenses | Total
|  | PM5 | Inspector 2 | Mileage
|  | 225.5403 | 127.2803 | 0.5
2024-2 Resurfacing Program
Reimbursable Expense i.e Mileage |  | 0 | 0 | 40 |  |  | 0 | 0 | 20
Project Management |  | 25 | 0 |  |  |  | 0 | 0 | 5638.5063
Preconstruction, Progress Meetings |  | 14 | [6 empty] | 3157.5635
Inspection / Measure / Quantify Items |  |  | 495 | [5 empty] | 63003.7478
Red-Line As-Built Drawings (required) & As-Built Digital Data Submission (if applicable) |  |  | 10 | [5 empty] | 1272.803
Final Construction Record | [8 empty] | 0
Subtotal |  | 39 | 505 | 40 | 0 | 0 | 0 | 0 | 73092.6206
Rounded Subtotal | [8 empty] | 73100
Total Cost | [8 empty] | 73100
Total Hours |  | 584

## Rate Sheet 3-3-2025
2024-2025 BILLING RATE TABLE
Overhead Effective Date: 07/01/23
Project Number & Description: 18-0114 - City of Lawrence - On-Call Engineering Services
GROUP CLASSIFICATIONS/STAFF TYPES | 2023 GROUP AVERAGE HOURLY LABOR RATE | 2023 AVERAGE HOURLY LABOR RATE X OVERHEAD @ | 2023 AVERAGE HOURLY LABOR RATE + OH | 2023 AVERAGE HOURLY LABOR RATE + OH x PROFIT @ | 2023 AVERAGE HOURLY LABOR RATE TIMES COST OF MONEY @ | 2023 HOURLY BILLING RATE | 2024 HOURLY BILLING RATE | 2025 HOURLY BILLING RATE | 2026 HOURLY BILLING RATE
|  | 194.2% |  | 15% | 0.47% |  | 3% | 3% | 3%
MANAGEMENT
Principal 7 | 86.222 | 167.4344 | 253.6564 | 38.0485 | 0.40524 | 292.1101 | 300.8734 | 309.8996 | 319.1966
ENGINEERING
Engineer 7 | 96.6504 | 187.6853 | 284.3357 | 42.6503 | 0.45426 | 327.4403 | 337.2635 | 347.3814 | 357.8028
Engineer 6 | 79.0685 | 153.5432 | 232.6117 | 34.8918 | 0.37162 | 267.8751 | 275.9114 | 284.1887 | 292.7144
Engineer 5 | 67.6616 | 131.3921 | 199.0537 | 29.858 | 0.31801 | 229.2297 | 236.1066 | 243.1898 | 250.4855
Engineer 4 | 58.3145 | 113.2409 | 171.5554 | 25.7333 | 0.27408 | 197.5627 | 203.4896 | 209.5943 | 215.8821
Engineer 3 | 46.6552 | 90.5997 | 137.2549 | 20.5882 | 0.21928 | 158.0625 | 162.8043 | 167.6885 | 172.7191
Engineer 2 | 44.2847 | 85.9965 | 130.2812 | 19.5422 | 0.20814 | 150.0315 | 154.5325 | 159.1685 | 163.9435
Engineer 1 | 34.8837 | 67.7408 | 102.6245 | 15.3937 | 0.16395 | 118.1821 | 121.7276 | 125.3794 | 129.1408
Designer 5 | 58.0086 | 112.6469 | 170.6555 | 25.5983 | 0.27264 | 196.5265 | 202.4223 | 208.4949 | 214.7498
Designer 4 | 49.2543 | 95.6469 | 144.9012 | 21.7352 | 0.2315 | 166.8679 | 171.8739 | 177.0302 | 182.3411
Designer 3 | 39.1267 | 75.9801 | 115.1067 | 17.266 | 0.1839 | 132.5566 | 136.5333 | 140.6293 | 144.8482
Designer 2 | 29.995 | 58.2473 | 88.2423 | 13.2363 | 0.14098 | 101.6196 | 104.6682 | 107.8082 | 111.0425
Designer 1 | 28.8413 | 56.007 | 84.8484 | 12.7273 | 0.13555 | 97.7112 | 100.6425 | 103.6618 | 106.7716
CADD Drafter 2 | 25.428 | 49.3786 | 74.8066 | 11.221 | 0.11951 | 86.1471 | 88.7316 | 91.3935 | 94.1353
CADD Drafter 1 | 21.2992 | 41.3609 | 62.6601 | 9.399 | 0.10011 | 72.1592 | 74.324 | 76.5537 | 78.8504
LANDSCAPE ARCHITECTURE
Landscape Architect 6 | 59.35 | 115.2518 | 174.6018 | 26.1903 | 0.27894 | 201.071 | 207.1031 | 213.3162 | 219.7157
Landscape Architect 5 | 51.7663 | 100.525 | 152.2913 | 22.8437 | 0.2433 | 175.3783 | 180.6396 | 186.0588 | 191.6406
Landscape Architect 4 | 39.81 | 77.307 | 117.117 | 17.5676 | 0.18711 | 134.8717 | 138.9179 | 143.0854 | 147.378
Landscape Architect 3 | 33.6539 | 65.3525 | 99.0064 | 14.851 | 0.15817 | 114.0155 | 117.436 | 120.9591 | 124.5879
Landscape Architect 2 | 32.9992 | 64.0811 | 97.0803 | 14.5621 | 0.1551 | 111.7975 | 115.1514 | 118.606 | 122.1641
Landscape Architect 1 | 27.56 | 53.5188 | 81.0788 | 12.1618 | 0.12953 | 93.3701 | 96.1712 | 99.0564 | 102.028
CONSTRUCTION SERVICES
Inspector 5 | 85.97 | 166.9451 | 252.9151 | 37.9373 | 0.40406 | 291.2565 | 299.9942 | 308.994 | 318.2638
Inspector 4 | 66.055 | 128.2722 | 194.3272 | 29.1491 | 0.31046 | 223.7867 | 230.5003 | 237.4154 | 244.5378
Inspector 3 | 42.618 | 82.7599 | 125.3779 | 18.8067 | 0.2003 | 144.3849 | 148.7164 | 153.1779 | 157.7733
Inspector 2 | 36.475 | 70.8308 | 107.3058 | 16.0959 | 0.17143 | 123.5731 | 127.2803 | 131.0987 | 135.0317
Inspector 1 | 27.4976 | 53.3976 | 80.8952 | 12.1343 | 0.12924 | 93.1587 | 95.9535 | 98.8321 | 101.797
SUPPORT
Administration 6 | 58.375 | 113.3585 | 171.7335 | 25.76 | 0.27436 | 197.7679 | 203.7009 | 209.8119 | 216.1063
Project Manager 5 | 64.6336 | 125.5119 | 190.1455 | 28.5218 | 0.30378 | 218.9711 | 225.5403 | 232.3065 | 239.2757
Administration 4 | 46.02 | 89.3662 | 135.3862 | 20.3079 | 0.21629 | 155.9105 | 160.5878 | 165.4054 | 170.3676
Administration 3 | 37.6314 | 73.0763 | 110.7077 | 16.6062 | 0.17687 | 127.4907 | 131.3155 | 135.2549 | 139.3126
Administration 2 | 26.845 | 52.1303 | 78.9753 | 11.8463 | 0.12617 | 90.9478 | 93.6762 | 96.4865 | 99.3811
Administration 1 | 22.36 | 43.4209 | 65.7809 | 9.8671 | 0.10509 | 75.7531 | 78.0257 | 80.3665 | 82.7775
Intern | 19.5 | 37.867 | 57.367 | 8.6051 | 0.09165 | 66.0638 | 68.0457 | 70.087 | 72.1897
As verified and Approved as to the date indicated.
Signed: ____________________________________________ | 2025-03-04 15:28

## 01 Hess Qty
Hess Qty's |  |  |  |  | Engineers Estimate |  | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left
ITEM |  |  | UNIT | QUANTITY | UNIT PRICE | AMOUNT | 2025-03-03
1 | 105-06845 | CONSTRUCTION ENGINEERING | LS | 1 | 4656.62 | 4656.62 | 0 | 1 | 0 | 4656.62 | 0 | 1 | 0 | 4656.62
2 | 110-01001 | MOBILIZATION AND DEMOBILIZATION | LS | 1 | 12230.61 | 12230.61 | 0 | 1 | 0 | 12230.61 | 0 | 1 | 0 | 12230.61
3 | 304-12623 | HMA PATCHING FULL DEPTH, TYPE B | TON | 165 | 165 | 27225 | 0 | 165 | 0 | 27225 | 0 | 165 | 0 | 27225
4 | 306-08038 | MILLING, ASPHALT, 4 IN. | SYS | 7836 | 3.5 | 27426 | 0 | 7836 | 0 | 27426 | 0 | 7836 | 0 | 27426
5 | 401-10258 | JOINT ADHESIVE, SURFACE | LFT | 1838 | 0.61 | 1121.18 | 0 | 1838 | 0 | 1121.18 | 0 | 1838 | 0 | 1121.18
6 | 401-10259 | JOINT ADHESIVE, INTERMEDIATE | LFT | 1838 | 0.61 | 1121.18 | 0 | 1838 | 0 | 1121.18 | 0 | 1838 | 0 | 1121.18
7 | 401-11785 | LIQUID ASPHALT SEALANT | LFT | 1838 | 0.35 | 643.3 | 0 | 1838 | 0 | 643.3 | 0 | 1838 | 0 | 643.3
8 | 401-99998 | HMA INTERMEDIATE, TYPE B | TON | 862 | 87.55 | 75468.1 | 0 | 862 | 0 | 75468.1 | 0 | 862 | 0 | 75468.1
9 | 401-99999 | HMA SURFACE, TYPE B | TON | 862 | 92.7 | 79907.4 | 0 | 862 | 0 | 79907.4 | 0 | 862 | 0 | 79907.4
10 | 406-05520 | ASPHALT FOR TACK COAT | TON | 3.9 | 55.31 | 215.709 | 0 | 3.9 | 0 | 215.709 | 0 | 3.9 | 0 | 215.709
11 | 801-06640 | CONSTRUCTION SIGN, A | EACH | 4 | 247.91 | 991.64 | 0 | 4 | 0 | 991.64 | 0 | 4 | 0 | 991.64
12 | 801-06775 | MAINTAINING TRAFFIC | LS | 1 | 7124.63 | 7124.63 | 0 | 1 | 0 | 7124.63 | 0 | 1 | 0 | 7124.63
TOTAL |  |  |  |  | 238131.369 |  |  |  | 0 | 238131.369 |  |  | 0 | 238131.369
Copy before adding new data (i.e) Daily Qty Tracker
[7 empty] | Contractor Signature |  |  |  | Contractor Signature
[7 empty] | Inspector Signature |  |  |  | Inspector Signature
[7 empty] | PM Signature |  |  |  | PM Signature

## 02 Paradise Qty
Paradise Qty's |  |  |  |  | Engineers Estimate |  | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left
ITEM |  |  | UNIT | QUANTITY | UNIT PRICE | AMOUNT |  |  |  |  | .
1 | 105-06845 | CONSTRUCTION ENGINEERING | LS | 1 | 399.15 | 399.15 | 0 | 1 | 0 | 399.15 | 0 | 1 | 0 | 399.15
2 | 110-01001 | MOBILIZATION AND DEMOBILIZATION | LS | 1 | 1048.37 | 1048.37 | 0 | 1 | 0 | 1048.37 | 0 | 1 | 0 | 1048.37
3 | 306-08599 | MILLING, ASPHALT, 1.5 IN. | SYS | 1879 | 2 | 3758 | 0 | 1879 | 0 | 3758 | 0 | 1879 | 0 | 3758
4 | 401-99999 | HMA SURFACE, TYPE B | TON | 153 | 92.7 | 14183.1 | 0 | 153 | 0 | 14183.1 | 0 | 153 | 0 | 14183.1
5 | 406-05520 | ASPHALT FOR TACK COAT | TON | 0.6 | 55.31 | 33.19 | 0 | 0.6 | 0 | 33.19 | 0 | 0.6 | 0 | 33.19
6 | 801-06640 | CONSTRUCTION SIGN, A | EACH | 8 | 247.91 | 1983.28 | 0 | 8 | 0 | 1983.28 | 0 | 8 | 0 | 1983.28
7 | 801-06775 | MAINTAINING TRAFFIC | LS | 1 | 610.7 | 610.7 | 0 | 1 | 0 | 610.7 | 0 | 1 | 0 | 610.7
TOTAL |  |  |  |  | 22015.79 |  |  |  | 0 | 22015.79 |  |  | 0 | 22015.79
Copy before adding new data (i.e) Daily Qty Tracker
[7 empty] | Contractor Signature |  |  |  | Contractor Signature
[7 empty] | Inspector Signature |  |  |  | Inspector Signature
[7 empty] | PM Signature |  |  |  | PM Signature

## 03 Broadway
Broadway Qty's |  |  |  |  | Engineers Estimate |  | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left
ITEM |  |  | UNIT | QUANTITY | UNIT PRICE | AMOUNT |  |  |  |  | .
1 | 105-06845 | CONSTRUCTION ENGINEERING | LS | 1 | 1860.95 | 1860.95 | 0 | 1 | 0 | 1860.95 | 0 | 1 | 0 | 1860.95
2 | 110-01001 | MOBILIZATION AND DEMOBILIZATION | LS | 1 | 4887.77 | 4887.77 | 0 | 1 | 0 | 4887.77 | 0 | 1 | 0 | 4887.77
5 | 304-12623 | HMA PATCHING FULL DEPTH, TYPE B | TON | 66 | 165 | 10890 | 0 | 66 | 0 | 10890 | 0 | 66 | 0 | 10890
6 | 306-08035 | MILLING, ASPHALT, 2 IN. | SYS | 5407 | 2 | 10814 | 0 | 5407 | 0 | 10814 | 0 | 5407 | 0 | 10814
7 | 306-08038 | MILLING, ASPHALT, 4 IN. | SYS | 305 | 3.5 | 1067.5 | 0 | 305 | 0 | 1067.5 | 0 | 305 | 0 | 1067.5
8 | 401-10258 | JOINT ADHESIVE, SURFACE | LFT | 2238 | 0.61 | 1365.18 | 0 | 2238 | 0 | 1365.18 | 0 | 2238 | 0 | 1365.18
9 | 401-10259 | JOINT ADHESIVE, INTERMEDIATE | LFT | 250 | 0.61 | 152.5 | 0 | 250 | 0 | 152.5 | 0 | 250 | 0 | 152.5
10 | 401-11785 | LIQUID ASPHALT SEALANT | LFT | 1838 | 0.35 | 643.3 | 0 | 1838 | 0 | 643.3 | 0 | 1838 | 0 | 643.3
11 | 401-99998 | HMA INTERMEDIATE, TYPE B | TON | 66 | 87.55 | 5778.3 | 0 | 66 | 0 | 5778.3 | 0 | 66 | 0 | 5778.3
12 | 401-99999 | HMA SURFACE, TYPE B | TON | 558 | 92.7 | 51726.6 | 0 | 558 | 0 | 51726.6 | 0 | 558 | 0 | 51726.6
13 | 406-05520 | ASPHALT FOR TACK COAT | TON | 4.5 | 55.31 | 248.9 | 0 | 4.5 | 0 | 248.9 | 0 | 4.5 | 0 | 248.9
14 | 801-06640 | CONSTRUCTION SIGN, A | EACH | 14 | 247.91 | 3470.74 | 0 | 14 | 0 | 3470.74 | 0 | 14 | 0 | 3470.74
15 | 801-06775 | MAINTAINING TRAFFIC | LS | 1 | 2847.25 | 2847.25 | 0 | 1 | 0 | 2847.25 | 0 | 1 | 0 | 2847.25
TOTAL |  |  |  |  | 95752.99 |  |  |  | 0 | 95752.99 |  |  | 0 | 95752.99
Copy before adding new data (i.e) Daily Qty Tracker
[5 empty] | Contractor Signature |  |  |  | Contractor Signature
[5 empty] | Inspector Signature |  |  |  | Inspector Signature
[5 empty] | PM Signature |  |  |  | PM Signature

## 04 Breckenridge
Breckenridge Qty's |  |  |  |  | Engineers Estimate |  | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left
ITEM |  |  | UNIT | QUANTITY | UNIT PRICE | AMOUNT |  |  |  |  | .
1 | 105-06845 | CONSTRUCTION ENGINEERING | LS | 1 | 7680.92 | 7680.92 | 0 | 1 | 0 | 7680.92 | 0 | 1 | 0 | 7680.92
2 | 110-01001 | MOBILIZATION AND DEMOBILIZATION | LS | 1 | 20173.93 | 20173.93 | 0 | 1 | 0 | 20173.93 | 0 | 1 | 0 | 20173.93
3 | 202-02279 | CURB AND GUTTER, REMOVE | LFT | 130 | 20.13 | 2616.9 | 0 | 130 | 0 | 2616.9 | 0 | 130 | 0 | 2616.9
4 | 202-52710 | SIDEWALK CONCRETE, REMOVE | SYS | 260 | 26.78 | 6962.8 | 0 | 260 | 0 | 6962.8 | 0 | 260 | 0 | 6962.8
5 | 304-12623 | HMA PATCHING FULL DEPTH, TYPE B | TON | 440 | 165 | 72600 | 0 | 440 | 0 | 72600 | 0 | 440 | 0 | 72600
6 | 306-08038 | MILLING, ASPHALT, 2 IN. | SYS | 17204 | 2 | 34408 | 0 | 17204 | 0 | 34408 | 0 | 17204 | 0 | 34408
7 | 401-10258 | JOINT ADHESIVE, SURFACE | LFT | 5035 | 0.61 | 3071.35 | 0 | 5035 | 0 | 3071.35 | 0 | 5035 | 0 | 3071.35
8 | 401-11785 | LIQUID ASPHALT SEALANT | LFT | 5035 | 0.35 | 1762.25 | 0 | 5035 | 0 | 1762.25 | 0 | 5035 | 0 | 1762.25
9 | 401-99999 | HMA SURFACE, TYPE B | TON | 2193 | 92.7 | 203291.1 | 0 | 2193 | 0 | 203291.1 | 0 | 2193 | 0 | 203291.1
10 | 406-05520 | ASPHALT FOR TACK COAT | TON | 4.5 | 55.31 | 248.9 | 0 | 4.5 | 0 | 248.9 | 0 | 4.5 | 0 | 248.9
11 | 604-06070 | SIDEWALK, CONCRETE | SYS | 130 | 92.19 | 11984.7 | 0 | 130 | 0 | 11984.7 | 0 | 130 | 0 | 11984.7
12 | 604-08086 | CURB RAMP, CONCRETE | SYS | 130 | 182.74 | 23756.2 | 0 | 130 | 0 | 23756.2 | 0 | 130 | 0 | 23756.2
13 | 604-12083 | DETECTABLE WARNING SURFACES | SYS | 19.5 | 315 | 6142.5 | 0 | 19.5 | 0 | 6142.5 | 0 | 19.5 | 0 | 6142.5
14 | 605-06140 | CURB AND GUTTER, CONCRETE | LFT | 130 | 65.53 | 8518.9 | 0 | 130 | 0 | 8518.9 | 0 | 130 | 0 | 8518.9
15 | 621-06575 | SODDING, NURSERY | SYS | 130 | 13.46 | 1749.8 | 0 | 130 | 0 | 1749.8 | 0 | 130 | 0 | 1749.8
16 | 801-06640 | CONSTRUCTION SIGN, A | EACH | 6 | 247.91 | 1487.46 | 0 | 6 | 0 | 1487.46 | 0 | 6 | 0 | 1487.46
17 | 801-06775 | MAINTAINING TRAFFIC | LS | 1 | 11751.8 | 11751.8 | 0 | 1 | 0 | 11751.8 | 0 | 1 | 0 | 11751.8
TOTAL |  |  |  |  | 418207.51 |  |  |  | 0 | 418207.51 |  |  | 0 | 418207.51
Copy before adding new data (i.e) Daily Qty Tracker
[7 empty] | Contractor Signature |  |  |  | Contractor Signature
[7 empty] | Inspector Signature |  |  |  | Inspector Signature
[7 empty] | PM Signature |  |  |  | PM Signature

## 05 53rd, Long, E Hill
Breckenridge Qty's |  |  |  |  | Engineers Estimate |  | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left
ITEM |  |  | UNIT | QUANTITY | UNIT PRICE | AMOUNT |  |  |  |  | .
1 | 105-06845 | CONSTRUCTION ENGINEERING | LS | 1 | 2052.44 | 2052.44 | 0 | 1 | 0 | 2052.44 | 0 | 1 | 0 | 2052.44
2 | 110-01001 | MOBILIZATION AND DEMOBILIZATION | LS | 1 | 5390.74 | 5390.74 | 0 | 1 | 0 | 5390.74 | 0 | 1 | 0 | 5390.74
3 | 202-02279 | CURB AND GUTTER, REMOVE | LFT | 40 | 20.13 | 805.2 | 0 | 40 | 0 | 805.2 | 0 | 40 | 0 | 805.2
4 | 202-52710 | SIDEWALK CONCRETE, REMOVE | SYS | 80 | 26.78 | 2142.4 | 0 | 80 | 0 | 2142.4 | 0 | 80 | 0 | 2142.4
5 | 304-12623 | HMA PATCHING FULL DEPTH, TYPE B | TON | 95 | 165 | 15675 | 0 | 95 | 0 | 15675 | 0 | 95 | 0 | 15675
6 | 306-08037 | MILLING, ASPHALT, 2 IN. | SYS | 5238 | 2 | 10476 | 0 | 5238 | 0 | 10476 | 0 | 5238 | 0 | 10476
7 | 401-10258 | JOINT ADHESIVE, SURFACE | LFT | 1488 | 0.61 | 907.68 | 0 | 1488 | 0 | 907.68 | 0 | 1488 | 0 | 907.68
8 | 401-11785 | LIQUID ASPHALT SEALANT | LFT | 1488 | 0.35 | 520.8 | 0 | 1488 | 0 | 520.8 | 0 | 1488 | 0 | 520.8
9 | 401-99999 | HMA SURFACE, TYPE B | TON | 577 | 92.7 | 53487.9 | 0 | 577 | 0 | 53487.9 | 0 | 577 | 0 | 53487.9
10 | 406-05520 | ASPHALT FOR TACK COAT | TON | 1.5 | 55.31 | 82.97 | 0 | 1.5 | 0 | 82.97 | 0 | 1.5 | 0 | 82.97
11 | 604-06070 | SIDEWALK, CONCRETE | SYS | 40 | 92.19 | 3687.6 | 0 | 40 | 0 | 3687.6 | 0 | 40 | 0 | 3687.6
12 | 604-08086 | CURB RAMP, CONCRETE | SYS | 40 | 182.74 | 7309.6 | 0 | 40 | 0 | 7309.6 | 0 | 40 | 0 | 7309.6
13 | 604-12083 | DETECTABLE WARNING SURFACES | SYS | 6 | 315 | 1890 | 0 | 6 | 0 | 1890 | 0 | 6 | 0 | 1890
14 | 605-06140 | CURB AND GUTTER, CONCRETE | LFT | 40 | 65.53 | 2621.2 | 0 | 40 | 0 | 2621.2 | 0 | 40 | 0 | 2621.2
15 | 621-06575 | SODDING, NURSERY | SYS | 40 | 13.46 | 538.4 | 0 | 40 | 0 | 538.4 | 0 | 40 | 0 | 538.4
16 | 801-06640 | CONSTRUCTION SIGN, A | EACH | 6 | 247.91 | 1487.46 | 0 | 6 | 0 | 1487.46 | 0 | 6 | 0 | 1487.46
17 | 801-06775 | MAINTAINING TRAFFIC | LS | 1 | 3140.24 | 3140.24 | 0 | 1 | 0 | 3140.24 | 0 | 1 | 0 | 3140.24
TOTAL |  |  |  |  | 112215.63 |  |  |  | 0 | 112215.63 |  |  | 0 | 112215.63
Copy before adding new data (i.e) Daily Qty Tracker
[7 empty] | Contractor Signature |  |  |  | Contractor Signature
[7 empty] | Inspector Signature |  |  |  | Inspector Signature
[7 empty] | PM Signature |  |  |  | PM Signature

## 06 E 52nd., Normal
Breckenridge Qty's |  |  |  |  | Engineers Estimate |  | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left | Daily qty Total per line item | Adjusted Qty Left | Paid Today | Contract Amount Left
ITEM |  |  | UNIT | QUANTITY | UNIT PRICE | AMOUNT |  |  |  |  | .
1 | 105-06845 | CONSTRUCTION ENGINEERING | LS | 1 | 1616.95 | 1616.95 | 0 | 1 | 0 | 1616.95 | 0 | 1 | 0 | 1616.95
2 | 110-01001 | MOBILIZATION AND DEMOBILIZATION | LS | 1 | 4246.92 | 4246.92 | 0 | 1 | 0 | 4246.92 | 0 | 1 | 0 | 4246.92
3 | 202-02279 | CURB AND GUTTER, REMOVE | LFT | 20 | 20.13 | 402.6 | 0 | 20 | 0 | 402.6 | 0 | 20 | 0 | 402.6
4 | 202-52710 | SIDEWALK, CONCRETE, REMOVE | SYS | 40 | 26.78 | 1071.2 | 0 | 40 | 0 | 1071.2 | 0 | 40 | 0 | 1071.2
5 | 304-12623 | HMA PATCHING FULL DEPTH, TYPE B | TON | 138 | 165 | 22770 | 0 | 138 | 0 | 22770 | 0 | 138 | 0 | 22770
6 | 306-08038 | MILLING, ASPHALT, 4 IN. | SYS | 4560 | 3.5 | 15960 | 0 | 4560 | 0 | 15960 | 0 | 4560 | 0 | 15960
7 | 401-10258 | JOINT ADHESIVE, SURFACE | LFT | 1170 | 0.61 | 713.7 | 0 | 1170 | 0 | 713.7 | 0 | 1170 | 1.1369e-13 | 713.7
8 | 401-10259 | JOINT ADHESIVE, INTERMEDIATE | LFT | 1170 | 0.61 | 713.7 | 0 | 1170 | 0 | 713.7 | 0 | 1170 | 1.1369e-13 | 713.7
9 | 401-11785 | LIQUID ASPHALT SEALANT | LFT | 1170 | 0.35 | 409.5 | 0 | 1170 | 0 | 409.5 | 0 | 1170 | 0 | 409.5
10 | 401-99998 | HMA INTERMEDIATE, TYPE B | TON | 501 | 87.55 | 43862.55 | 0 | 501 | 0 | 43862.55 | 0 | 501 | 0 | 43862.55
11 | 401-99999 | HMA SURFACE, TYPE B | TON | 501 | 92.7 | 46442.7 | 0 | 501 | 0 | 46442.7 | 0 | 501 | 0 | 46442.7
12 | 406-05520 | ASPHALT FOR TACK COAT | TON | 2.25 | 55.31 | 124.45 | 0 | 2.25 | 0 | 124.45 | 0 | 2.25 | 0 | 124.45
13 | 604-06070 | SIDEWALK, CONCRETE | SYS | 20 | 62.19 | 1243.8 | 0 | 20 | 0 | 1243.8 | 0 | 20 | 0 | 1243.8
14 | 604-08086 | CURB RAMP, CONCRETE | SYS | 20 | 182.74 | 3654.8 | 0 | 20 | 0 | 3654.8 | 0 | 20 | 0 | 3654.8
15 | 604-12083 | DETECTABLE WARNING SURFACE | SYS | 3 | 315 | 945 | 0 | 3 | 0 | 945 | 0 | 3 | 0 | 945
16 | 605-06140 | CURB AND GUTTER, CONCRETE | LFT | 20 | 65.53 | 1310.6 | 0 | 20 | 0 | 1310.6 | 0 | 20 | 0 | 1310.6
17 | 621-06575 | SODDING, NURSERY | SYS | 20 | 13.46 | 269.2 | 0 | 20 | 0 | 269.2 | 0 | 20 | 0 | 269.2
18 | 801-06640 | CONSTRUCTION SIGN, A | EACH | 6 | 247.91 | 1487.46 | 0 | 6 | 0 | 1487.46 | 0 | 6 | 0 | 1487.46
19 | 801-06775 | MAINTAINING TRAFFIC | LS | 1 | 2473.93 | 2473.93 | 0 | 1 | 0 | 2473.93 | 0 | 1 | 0 | 2473.93
TOTAL |  |  |  |  | 149719.06 |  |  |  | 0 | 149719.06 |  |  | 2.2737e-13 | 149719.06
Copy before adding new data (i.e) Daily Qty Tracker
[5 empty] | Contractor Signature |  |  |  | Contractor Signature
[5 empty] | Inspector Signature |  |  |  | Inspector Signature
[5 empty] | PM Signature |  |  |  | PM Signature